## Example1
Example - Tracking - Decision Master
Action 4 buttons
Search | 1. Input 7 Objects |  |  | 0.25 | Man-Day
| 2. Search button - Function Search API - Input 6 Output 10 objects |  |  | 0.5 | Man-Day
(16 Objects)
Grid table | 11 Column |  |  | 0.5 | Man-Day
Add-Popup
| 1. Input 9 Objects |  |  | 0.25 | Man-Day
| 2. Comboobx-API 2 Objects |  | 2 | 0.5 | Man-Day
| 3. Save button - Function - Validate - Javascript |  |  | 0.25 | Man-Day
| 4. Save button - Function - Add - API |  |  | 0.25 | Man-Day
Edit-Popup | Reuse - Add Object and Function
1. Input 9 Objects
2. Comboobx-API 2 Objects
3. Save button - Function - Validate - Javascript
| 4. Show data - Function - Get data - API |  |  | 0.25 | Man-Day
| 5. Save button - Function - Update - API |  |  | 0.25 | Man-Day
Delete-Popup | 1. Confirm text |  |  | 0.25 | Man-Day
| 2. Confirm button - Function Delete API |  |  | 0.25 | Man-Day
Summary Man-Day - Tracking - Decision Master
Module | Task |  |  | Man-Day
Search | 1. Input 7 Objects |  |  | 0.25
| 2. Search button - Function Search API - Input 6 Output 10 objects (16 objects) |  |  | 0.5
Grid table | 1. 11 Column |  |  | 0.5
Add-Popup | 1. Input 9 Objects |  |  | 0.25
| 2. Comboobx-API 2 Objects |  |  | 0.5
| 3. Save button - Function - Validate - Javascript |  |  | 0.25
| 4. Save button - Function - Add - API |  |  | 0.25
Edit-Popup | 1. Input 9 Objects |  | Reuse
| 2. Comboobx-API 2 Objects |  | Reuse
| 3. Save button - Function - Validate - Javascript |  | Reuse
| 4. Show data - Function - Get data API |  |  | 0.25
| 5. Save button - Function - Update - API |  |  | 0.25
Delete-Popup | 1. Confirm text |  |  | 0.25
| 2. Confirm button - Function Delete API |  |  | 0.25
| Summary |  |  | 3.5

## Example2
Example - Tracking - Confirmation Entry
Action 2 buttons
Search | 1. Input 16 Objects | 0.5 | Man-Day
| 2. Combobox - API 6 Objects | 1.5 | Man-Day
| 3. Search button - Function Search API - Input 14 objects Output 19 objects (33 objects) | 2 | Man-Day
| 4. Clear button - Function clear input - Javascript | 0.25 | Man-Day
Grid Table | 19 Column | 0.5 | Man-Day
Summary Man-Day - Tracking - Confirmation Entry
Module | Task | Man-Day
Search | 1. Input 16 Objects | 0.5
| 2. Combobox - API 6 Objects | 1.5
| 3. Search button - Function Search API - Input 14 objects Output 19 objects (33 objects) | 2
| 4. Clear button - Function clear input - Javascript | 0.25
Grid table | 1. 19 Column | 0.5
| Summary | 4.75

## SA Authorization - JIRA (hidden)
Key | Summary | Ticket Type | Target start | Target end | Assignee | Status | Story Points | PIC
AD-2315 | Database design | Coding | 2020-06-18 | 2020-06-18 | Jaruwat Tongpanya | Open | 2 | AD
AD-2322 | EF Daily Report - SA Permission | Coding | 2020-06-19 | 2020-06-19 | Jaruwat Tongpanya | Open | 2 | AD
AD-2323 | CM Daily Report - SA Permission | Coding | 2020-06-22 | 2020-06-22 | Jaruwat Tongpanya | Open | 2 | AD
AD-2324 | Front Inquiry and Entry - SA Permission | Coding | 2020-06-22 | 2020-06-23 | Jaruwat Tongpanya | Open | 3 | AD
AD-2325 | Confirmation Inquiry / Entry / Cancel - SA Permission | Coding | 2020-06-24 | 2020-06-25 | Jaruwat Tongpanya | Open | 4 | AD
AD-2326 | Leadtime Report - SA Permission | Coding | 2020-06-26 | 2020-06-26 | Jaruwat Tongpanya | Open | 2 | AD
AD-2327 | Sale Overview Report - SA Permission | Coding | 2020-06-27 | 2020-06-27 | Jaruwat Tongpanya | Open | 2 | AD
AD-2328 | Tracking Report - SA Permission | Coding | 2020-06-29 | 2020-06-29 | Jaruwat Tongpanya | Open | 2 | AD
AD-2319 | Enhance and bug fix - UAT | Coding | 2020-07-07 | 2020-07-07 | Jaruwat Tongpanya | Open | 2 | AD
AD-2318 | Production and Instruction Deploy | Production | 2020-07-02 | 2020-07-02 | Jaruwat Tongpanya | Open | 2 | AD
AD-2321 | Publishing Website (Go-Live) | Production | 2020-07-09 | 2020-07-09 | Jaruwat Tongpanya | Open | 1 | AS
AD-2313 | Get requirement with User (SC) | Requirement | 2020-06-16 | 2020-06-16 | Jaruwat Tongpanya | Open | 2 | AD
AD-2314 | Confirm mockup and design | Requirement | 2020-06-17 | 2020-06-17 | Jaruwat Tongpanya | Open | 2 | AD
AD-2316 | SA Authentication Mode - SIT | SIT | 2020-06-30 | 2020-07-01 | Jaruwat Tongpanya | Open | 4 | AD
AD-2317 | SA Authentication Mode - UAT | UAT | 2020-07-03 | 2020-07-06 | Jaruwat Tongpanya | Open | 4 | SC
AD-2320 | Re-test and confirm final UAT result | UAT | 2020-07-08 | 2020-07-08 | Jaruwat Tongpanya | Open | 2 | SC
38

## DealerTracking_JIRA (hidden)
Key | Summary | Ticket Type | Target start | Target end | Assignee | Status | Actual Date | Story Points | PIC
AD-2285 | Database design | Coding | 2020-03-02 | 2020-03-02 | Jaruwat Tongpanya | Closed | 2020-03-02 | 2 | AD
AD-1980 | Dealer authentication | Coding | 2020-03-03 | 2020-03-04 | Jaruwat Tongpanya | Closed | 2020-03-04 | 4 | AD
AD-2016 | Dealer transaction log | Coding | 2020-03-10 | 2020-03-10 | Jaruwat Tongpanya | Closed | 2020-03-10 | 2 | AD
AD-2024 | Dealer Login Master - Table result incorrect | Coding | 2020-03-12 | 2020-03-12 | Jaruwat Tongpanya | Closed | 2020-03-12 | 2 | AD
AD-2038 | Show report by dealer outlet | Coding | 2020-03-17 | 2020-03-17 | Jaruwat Tongpanya | Closed | 2020-03-17 | 2 | AD
AD-2035 | User account active via email | Coding | 2020-03-19 | 2020-03-20 | Jaruwat Tongpanya | Closed | 2020-03-20 | 2 | AD
AD-2037 | Alter database for reset, login fail, expire password | Coding | 2020-03-23 | 2020-03-23 | Jaruwat Tongpanya | Closed | 2020-03-23 | 2 | AD
AD-1981 | Dealer Login Master - Search incorrect | Coding | 2020-05-05 | 2020-05-05 | Jaruwat Tongpanya | Closed | 2020-05-05 | 2 | AD
AD-2034 | Email notification for Activate and Reset Password | Coding | 2020-05-07 | 2020-05-08 | Jaruwat Tongpanya | Closed | 2020-05-11 | 4 | AD
AD-2254 | Dealer change password | Coding | 2020-05-07 | 2020-05-08 | Jaruwat Tongpanya | Closed | 2020-05-08 | 4 | AD
AD-2036 | Force change password (reset code) | Coding | 2020-05-11 | 2020-05-12 | Jaruwat Tongpanya | Closed | 2020-05-12 | 3 | AD
AD-2273 | Enhance Web UI to support responsive | Coding | 2020-05-13 | 2020-05-14 | Jaruwat Tongpanya | Closed | 2020-05-15 | 4 | AD
AD-2305 | Notification password will expire (7 Days) | Coding | 2020-05-20 | 2020-05-20 | Jaruwat Tongpanya | Closed | 2020-05-20 | 2 | AD
AD-2308 | Modify database and generate entity framework model | Coding | 2020-05-22 | 2020-05-22 | Jaruwat Tongpanya | Open |  | 2 | AD
AD-2271 | Enhance Decision Master | Coding | 2020-05-25 | 2020-05-26 | Jaruwat Tongpanya | Open |  | 4 | AD
AD-2270 | Enhance Lead-time Report | Coding | 2020-05-27 | 2020-05-29 | Jaruwat Tongpanya | Open |  | 6 | AD
AD-2279 | Enhance and bug fix - UAT | Coding | 2020-05-29 | 2020-05-29 | Jaruwat Tongpanya | Open |  | 2 | AD
AD-2281 | Fix security bug | Coding | 2020-06-03 | 2020-06-11 | Jaruwat Tongpanya | To Do |  | 4 | AD
AD-2050 | Production and Instruction Deploy | Production | 2020-06-01 | 2020-06-01 | Jaruwat Tongpanya | Open |  | 2 | AD
AD-2224 | Penetration Testing | Production | 2020-06-01 | 2020-06-11 | Jaruwat Tongpanya | Open |  | 6 | AD
AD-2282 | Publishing Website (Go-Live) | Production | 2020-06-11 | 2020-06-11 | Jaruwat Tongpanya | Open |  | 1 | AD
AD-2306 | Register new menu in the matrix & user request for access | Production | 2020-06-11 | 2020-06-12 | Unassigned | Open |  | 1 | SP,IF
AD-2283 | Get requirement with User (SP, SC) | Requirement | 2020-02-28 | 2020-02-28 | Jaruwat Tongpanya | Closed | 2020-03-02 | 2 | AD
AD-2284 | Confirm mockup and design | Requirement | 2020-02-29 | 2020-02-29 | Jaruwat Tongpanya | Closed | 2020-03-02 | 2 | AD
AD-1982 | Support GCP committee presentation (SP) | Requirement | 2020-03-03 | 2020-03-03 | Jaruwat Tongpanya | Closed | 2020-03-03 | 2 | AD
AD-2021 | Dealer activate account diagram | Requirement | 2020-03-09 | 2020-03-09 | Jaruwat Tongpanya | Closed | 2020-03-09 | 1 | AD
AD-2027 | Mock-up and screen for email notification | Requirement | 2020-03-12 | 2020-03-12 | Jaruwat Tongpanya | Closed | 2020-03-12 | 1 | AD
AD-2272 | Confirm workflow and new requirement with SP, SC (J1,J2) | Requirement | 2020-05-15 | 2020-05-18 | Jaruwat Tongpanya | Closed | 2020-05-18 | 4 | AD
AD-2307 | Confirm new decision master with User | Requirement | 2020-05-21 | 2020-05-21 | Jaruwat Tongpanya | Open |  | 2 | AD
AD-2223 | Dealer Status Tracking - SIT | SIT | 2020-05-25 | 2020-05-31 | Jaruwat Tongpanya | Open |  | 4 | AD
AD-2049 | Dealer Status Tracking - UAT | UAT | 2020-05-27 | 2020-05-28 | Jaruwat Tongpanya | Open |  | 4 | AD
AD-2280 | Re-test and confirm final UAT result | UAT | 2020-05-29 | 2020-05-30 | Jaruwat Tongpanya | Open |  | 2 | AD

## CI_CD_JIRA (hidden)
Key | Summary | Target start | Target end | Actual Date | Assignee | Owner | Status | Story Points | Priority | PIC
AD-2177 | CI/CD Infrastructure Diagram | 2020-04-23 | 2020-04-23 | 2020-04-23 | Jaruwat Tongpanya |  | Closed | 1 | Medium | AD
AD-2180 | Prepare server and install software - IF | 2020-06-01 | 2020-07-10 |  | Jaruwat Tongpanya |  | Open | 34 | Blocker | IF
AD-2190 | Restructure source code to support CI/CD | 2020-06-22 | 2020-07-03 |  | Jaruwat Tongpanya |  | Open | 20 | High | AD
AD-2193 | Authorization User and Server (IF) | 2020-07-06 | 2020-07-10 |  | Jaruwat Tongpanya |  | Open | 10 | High | AD
AD-2188 | .NET Unit Test Example | 2020-07-06 | 2020-07-10 |  | Jaruwat Tongpanya |  | Open | 10 | High | AD
AD-2191 | Move Jira to CI/CD Server | 2020-07-10 | 2020-07-14 |  | Jaruwat Tongpanya |  | Open | 6 | High | IF
AD-2179 | Configuration TeamCity integrate TFS | 2020-07-15 | 2020-07-17 |  | Jaruwat Tongpanya |  | Open | 6 | High | AD
AD-2187 | Configuration TeamCity integrate Jira | 2020-07-20 | 2020-07-21 |  | Jaruwat Tongpanya |  | Open | 4 | High | AD
AD-2183 | Configuration TeamCity integrate Sonarqube | 2020-07-22 | 2020-07-27 |  | Jaruwat Tongpanya |  | Open | 10 | High | AD
AD-2181 | Configuration TeamCity integrate Octopus | 2020-07-28 | 2020-08-03 |  | Jaruwat Tongpanya |  | Open | 10 | High | AD
AD-2182 | Configuration Octopus Deployment | 2020-08-04 | 2020-08-10 |  | Jaruwat Tongpanya |  | Open | 10 | High | AD
AD-2185 | Prepare document training | 2020-08-05 | 2020-08-11 |  | Jaruwat Tongpanya |  | Open | 10 | High | AD
AD-2184 | Training CI/CD Team | 2020-08-12 | 2020-08-12 |  | Jaruwat Tongpanya |  | Open | 2 | High | AD
AD-2186 | Golive CI/CD | 2020-08-13 | 2020-08-13 |  | Jaruwat Tongpanya |  | Open | 2 | High | AD
AD-2189 | Coordinate prepare server and test with IF | 2020-06-15 | 2020-07-10 |  | Jaruwat Tongpanya |  | Open | 10 | Blocker | AD